## Quick Reference
Prompt Quick Reference — 02 Stakeholder Management
Ahmed Elsayyad ¦ Senior Business Analyst ¦ Elsayyad Digital Solutions ¦ ahmedelsayyad006@gmail.com ¦ Cairo, Egypt
# | Prompt Name | Purpose | Use Case | Required Inputs | Ready-to-Use Prompt | Example Input | Best Practices | Advanced Version | Expert Tips
1 | Stakeholder Identification Prompt | Identify all stakeholders for a project | Project kick-off, stakeholder analysis | Project description, organization type | Act as a Senior BA. Identify all stakeholders for this project: [PROJECT]. Categorize them as: Internal/External, Primary/Secondary, and by their relationship (Decision Maker, Influencer, End User, Subject Matter Expert, Regulator). Create a stakeholder identification table. | Project: Implementing an online customer support portal for Elsayyad Digital Solutions. | Cast a wide net in the first pass. You can always narrow down — missing a stakeholder is harder to recover from. | Identify stakeholders AND map their influence network, communication preferences, and potential conflicts for: [PROJECT]. Output as a Stakeholder Universe Map. | Hidden stakeholders (legal, compliance, support) are the ones who derail projects. Find them early.
2 | Power-Interest Matrix Generator | Map stakeholders on a Power-Interest matrix | Stakeholder engagement planning, communication strategy | Stakeholder list with power and interest levels | Act as a Senior BA. Map the following stakeholders on a Power-Interest Matrix. Assign each a quadrant (Manage Closely / Keep Satisfied / Keep Informed / Monitor) and recommend an engagement strategy for each. Stakeholders: [LIST]. | Stakeholders: CEO (High Power, Low Interest), IT Manager (High Power, High Interest), End Users (Low Power, High Interest), Legal Team (High Power, Low Interest). | Update the matrix monthly — stakeholder power and interest shift during projects. | Generate a Power-Interest Matrix AND a tailored Communication Plan for each quadrant with frequency, channel, message type, and owner for: [PROJECT]. | The most dangerous stakeholder is the one in 'Monitor' who suddenly moves to 'Manage Closely.' Check this monthly.
3 | Stakeholder Register Builder | Build a comprehensive stakeholder register | Project documentation, governance, BA planning | Project name, stakeholder list, roles | Act as a Senior BA. Build a Stakeholder Register for: Project: [PROJECT]. For each stakeholder include: Name, Role, Organization, Contact, Level of Interest (H/M/L), Level of Influence (H/M/L), Engagement Strategy, Communication Preference, Current Attitude (Champion/Neutral/Resistant), and Key Concerns. | Project: CRM system implementation at Elsayyad Digital Solutions. | Keep the register updated as a living document. Assign an owner for each stakeholder. | Build a Stakeholder Register AND a Stakeholder Engagement Assessment Matrix (SEAM) with current and target engagement levels and action plans for: [PROJECT]. | A stale stakeholder register is worse than no register. Review and update it monthly.
4 | RACI Matrix Generator | Create a RACI matrix for a project or process | Project governance, team alignment, decision-making | Activity list, team members and roles | Act as a Senior BA. Create a RACI Matrix for: Project/Process: [NAME]. Activities: [LIST]. Team Members: [LIST]. Assign R (Responsible), A (Accountable), C (Consulted), I (Informed) for each activity-person combination. Flag any accountability gaps. | Process: Requirements Sign-Off Process. Team: Ahmed Elsayyad (BA), Project Manager, IT Manager, Business Owner, Legal. | Every activity must have exactly one A (Accountable). Multiple R's are fine, but no R means work won't get done. | Generate a RACI Matrix AND a Decision Rights Matrix (DACI) for all key project decisions in: [PROJECT]. Identify conflicts and resolution paths. | RACI without a conversation is just a spreadsheet. Validate it with the team in a meeting.
5 | Stakeholder Engagement Plan | Create a stakeholder engagement plan | Communication planning, project governance | Stakeholder register, project timeline | Act as a Senior BA. Create a Stakeholder Engagement Plan for: Project: [PROJECT]. Based on this stakeholder list: [LIST]. Include: engagement objectives, activities, frequency, channels, responsible person, and success metrics for each stakeholder group. | Project: Digital HR system rollout at Elsayyad Digital Solutions. Stakeholders: HR team, IT, Finance, 150 employees. | Engagement plans must be reviewed and updated at each project phase. | Create a Stakeholder Engagement Plan with a Communication Calendar, escalation path, feedback mechanism, and resistance management strategy for: [PROJECT]. | Engagement is not communication — it's two-way. Build feedback loops into your plan.
6 | Stakeholder Interview Preparation | Prepare for a stakeholder interview | Elicitation planning, discovery sessions | Stakeholder role, information needed, project context | Act as a Senior BA. Prepare me for an interview with: Stakeholder: [ROLE]. Project: [PROJECT]. Goal: [GOAL]. Generate: 10 open-ended questions, 5 probing follow-up questions, interview agenda, and tips for managing this stakeholder type. | Stakeholder: CFO. Project: Finance reporting automation. Goal: Understand reporting pain points and ROI expectations. | Send the agenda in advance. Take a note-taker if possible. Never lead with solution ideas. | Prepare a full interview kit for [STAKEHOLDER] including: question bank, stakeholder profile, active listening guide, note-taking template, and post-interview debrief checklist. | The best interview question is 'Can you walk me through a typical day/week doing this?' — it reveals everything.
7 | Persona Creator | Create a detailed user persona | Product design, requirements gathering, UX analysis | User type, demographics, goals, pain points | Act as a Senior BA and UX Analyst. Create a detailed user persona for: User Type: [TYPE]. System/Product: [SYSTEM]. Include: Name, Photo description, Demographics, Job Title, Goals, Frustrations, Technology comfort, Typical tasks, Quote, and How the system should serve them. | User Type: Field Sales Representative. System: Mobile CRM application. | Validate personas with real users — don't create them from assumptions alone. | Generate 3 distinct personas for [SYSTEM] and create a Persona-to-Requirements mapping showing which features serve which persona, prioritized by business value. | Personas turn abstract users into real people — they make requirements conversations much richer.
8 | Resistance Management Plan | Identify and manage stakeholder resistance | Change management, project delivery, stakeholder engagement | Resistant stakeholder description, nature of resistance | Act as a Senior BA and Change Management Expert. A stakeholder is resisting the project: Stakeholder: [ROLE]. Nature of resistance: [DESCRIPTION]. Project: [PROJECT]. Generate: Root cause analysis of resistance, engagement strategy, communication approach, and escalation path if resistance continues. | Stakeholder: IT Manager. Resistance: Does not want to migrate to cloud (prefers on-premise). Project: Cloud ERP implementation. | Resistance is almost never about the technology — it's about people's fears. Address the person, not the position. | Generate a Change Resistance Analysis for all high-resistance stakeholders in [PROJECT] with a PROSCI ADKAR-based engagement plan for each. | Resistant stakeholders who become champions are your most powerful advocates. Invest time in them.
9 | Communication Plan Builder | Build a stakeholder communication plan | Project governance, team alignment, reporting structure | Stakeholder list, project phases, communication preferences | Act as a Senior BA. Build a Communication Plan for: Project: [PROJECT]. Stakeholders: [LIST]. Include: Who receives what communication, format, frequency, channel, owner, and escalation path. Create a communication calendar for the first month. | Project: Customer Portal Launch. Stakeholders: Exec team, Product team, IT, customers, CS team. | Communication plans must match the recipient's preference — some executives want a 1-page summary, not a 10-page report. | Build a Communication Plan with message templates, escalation triggers, feedback loops, and a 90-day communication calendar for: [PROJECT]. | Over-communication on big projects is almost impossible. Under-communication is very easy.
10 | Stakeholder Conflict Resolver | Resolve conflicts between stakeholders | Requirements conflicts, priority disputes, scope disagreements | Conflicting parties, nature of conflict, project context | Act as a Senior BA and facilitator. Two stakeholders have conflicting requirements: Stakeholder A: [REQUIREMENT A]. Stakeholder B: [REQUIREMENT B]. Project: [PROJECT]. Generate: conflict analysis, facilitation strategy, resolution options, and recommended decision framework. | Stakeholder A (Sales): System must allow unlimited discount levels. Stakeholder B (Finance): Discounts must be capped at 20%. Project: Order management system. | Never take sides in a stakeholder conflict. Present options with trade-offs. Let the sponsor decide. | Generate a Conflict Resolution Playbook for common BA conflicts (requirements, priority, scope, resources) with facilitation scripts and escalation paths for: [PROJECT TYPE]. | Most stakeholder conflicts are about fear and control, not the actual requirement. Listen for what's unsaid.
11 | Stakeholder Analysis Report | Generate a stakeholder analysis report | Executive reporting, governance, project kick-off | Project name, stakeholder data | Act as a Senior BA. Write a Stakeholder Analysis Report for: Project: [PROJECT]. Cover: stakeholder universe, influence mapping, engagement levels, risks, and recommended actions. Format for executive audience. | Project: New ERP at Elsayyad Digital Solutions. | Keep executive reports to 1-2 pages. Append detail in annexes. | Generate a full Stakeholder Analysis Report with influence network diagram description, engagement heat map, and a 90-day stakeholder engagement action plan. | A stakeholder analysis is not a one-time exercise. Repeat it at every project phase.
12 | Stakeholder Survey Designer | Design a stakeholder survey for requirement gathering | Large-scale elicitation, user research, feedback collection | Survey objective, target audience, topics | Act as a Senior BA. Design a [DURATION] survey for: Objective: [OBJECTIVE]. Audience: [AUDIENCE]. Topics: [TOPICS]. Include: 10-15 questions, question type (multiple choice, Likert, open-ended), and analysis guidance. | Objective: Understand finance team's reporting pain points. Audience: 20 finance staff. Topics: Current process, pain points, ideal future state. | Keep surveys under 10 minutes. Pilot test with 2-3 users before sending. | Design a survey AND create an analysis template, automated summary prompt, and follow-up interview questions based on expected survey results for: [OBJECTIVE]. | Open-ended questions give you insight. Closed questions give you data. You need both.
13 | Change Impact Assessment | Assess the impact of a change on stakeholders | Change management, impact analysis, communication planning | Change description, affected stakeholders, timeline | Act as a Senior BA. Perform a Change Impact Assessment for: Change: [DESCRIPTION]. Affected Stakeholders: [LIST]. Timeline: [TIMELINE]. For each stakeholder group, assess: What changes for them, degree of impact (High/Medium/Low), support needed, communication approach. | Change: Moving from manual expense reports (paper) to digital expense management system. Stakeholders: 150 employees, Finance team, IT. | Always quantify the impact — number of people affected, process steps changed, training hours needed. | Generate a Change Impact Assessment AND a Change Management Plan with ADKAR milestones, training plan, and resistance mitigation for: [CHANGE]. | Impact assessment without a management plan is just a warning. Always follow up with action.
14 | Stakeholder Sign-Off Preparation | Prepare stakeholders for document sign-off | Requirements baseline, BRD approval, UAT sign-off | Document type, stakeholder list, review timeline | Act as a Senior BA. Prepare a sign-off package for: Document: [DOCUMENT]. Stakeholders: [LIST]. Timeline: [TIMELINE]. Include: cover email, review guide, sign-off form, FAQ for stakeholders, and escalation plan if sign-off is delayed. | Document: Business Requirements Document v1.0. Stakeholders: Business Owner, IT Manager, Legal. Timeline: 5 business days. | Set a deadline and a reminder. Never leave sign-off open-ended. | Create a full sign-off management process including: review tracking dashboard, reminder schedule, escalation matrix, and version control process for: [PROJECT]. | No sign-off = no baseline. No baseline = unlimited scope creep.
15 | Executive Briefing Preparer | Prepare an executive briefing on a project | Executive communication, status reporting, decision escalation | Project status, key decisions needed, risks | Act as a Senior BA. Prepare a 1-page executive briefing for: Project: [PROJECT]. Status: [STATUS]. Key Decisions Needed: [DECISIONS]. Top Risks: [RISKS]. Format: BLUF (Bottom Line Up Front), status summary, decisions required, risk table, and next steps. | Project: ERP Migration. Status: Discovery phase complete, 2 weeks ahead of schedule. Decision needed: Vendor selection between SAP and Oracle. Risk: Budget may exceed by 15%. | Executives read the first 3 sentences and the last bullet. Make them count. | Generate an Executive Dashboard for [PROJECT] with: RAG status, milestone timeline, financial summary, top 3 risks, and key decisions — all in a single visual-friendly page. | Never bring a problem to an executive without a recommendation. Even if you're not sure, present your best option.
16 | Stakeholder Feedback Analyzer | Analyze stakeholder feedback from reviews or surveys | Requirements refinement, retrospective analysis | Feedback text or survey results | Act as a Senior BA. Analyze the following stakeholder feedback. Categorize themes, identify patterns, flag critical concerns, and recommend actions. Feedback: [FEEDBACK TEXT]. | Feedback: 'The report is too complex.' 'I can't find the export button.' 'Response time is too slow.' 'The dashboard is great but I need it on mobile.' 'Not enough training.' | Quantify feedback where possible. Track themes across multiple feedback cycles. | Analyze feedback AND generate a prioritized Product Backlog based on stakeholder themes, business impact, and frequency for: [FEEDBACK DATASET]. | Feedback is a gift. The stakeholders who complain are telling you how to succeed.
17 | Onboarding Stakeholder Brief | Create an onboarding brief for a new stakeholder | New stakeholder joining mid-project, team transitions | Project overview, stakeholder role, current status | Act as a Senior BA. Create an onboarding brief for a new stakeholder joining the project: Project: [PROJECT]. New Stakeholder: [ROLE]. Current Status: [STATUS]. Cover: project background, objectives, current progress, their role, key contacts, next steps. | Project: Customer portal. New stakeholder: IT Security Manager. Status: Design phase, security review pending. | Send the onboarding brief 48h before the stakeholder's first meeting. | Create a Stakeholder Onboarding Kit including: project brief, stakeholder register, key document index, decision log, and first-week meeting schedule for new stakeholders joining [PROJECT] at [PHASE]. | A well-onboarded stakeholder becomes an asset. A poorly onboarded one becomes a problem.
18 | Stakeholder Escalation Path Designer | Design an escalation path for stakeholder issues | Governance, conflict resolution, project management | Issue types, stakeholder hierarchy, response time requirements | Act as a Senior BA. Design an Escalation Path for: Project: [PROJECT]. Common issues: [ISSUE TYPES]. Stakeholder hierarchy: [HIERARCHY]. Include: escalation levels, triggers, response time SLAs, and resolution documentation process. | Project: ERP implementation. Issues: Scope disputes, requirement conflicts, technical blockers, budget changes. Hierarchy: BA → PM → Business Owner → Steering Committee → CEO. | Escalation paths prevent issues from dying in inbox limbo. Document and publish them. | Design a full Project Governance Framework including escalation path, decision rights matrix, issue log template, and resolution tracking process for: [PROJECT]. | Escalation is not failure — it's governance. Build it in from day one.
19 | Meeting Agenda for Stakeholder Workshop | Create a professional meeting agenda for stakeholder sessions | Workshop planning, meeting facilitation | Meeting objective, participants, duration | Act as a Senior BA. Create a detailed meeting agenda for: Meeting: [TYPE]. Objective: [OBJECTIVE]. Participants: [LIST]. Duration: [DURATION]. Include: agenda items, time allocations, responsible person, preparation required, and expected outputs. | Meeting: Requirements Review Workshop. Objective: Review and approve draft requirements for phase 1. Participants: Ahmed Elsayyad (BA), Business Owner, IT Manager, Legal. Duration: 2 hours. | Send agenda 48h in advance. Assign pre-read materials. Keep to schedule ruthlessly. | Generate a full Workshop Facilitation Pack including: pre-read, agenda, facilitation guide, exercise templates, note-taking template, and post-workshop action log for: [WORKSHOP TYPE]. | A meeting without an agenda is just a conversation. A meeting with a great agenda is where requirements get made.
20 | Stakeholder Training Needs Assessment | Assess training needs for stakeholders on a new system | Change management, go-live preparation, user adoption | System name, stakeholder groups, current skill levels | Act as a Senior BA. Perform a Training Needs Assessment for: System: [SYSTEM]. Stakeholder groups: [GROUPS]. Assess: current skill level, required skill level, training gap, recommended training format, duration, and priority. | System: New CRM system. Groups: Sales team (20 people), Sales Managers (5), IT support (3). | Always pilot training with a small group first. Gather feedback before rolling out. | Generate a full Training Plan with schedule, trainer assignments, materials checklist, competency assessment, and post-training evaluation for: [SYSTEM ROLLOUT]. | Training without follow-up support leads to adoption failure. Build a help desk and FAQ alongside training.
Design & Prepared by: | Ahmed El Sayyad

## Prompt Index
Prompt Index — 02 Stakeholder Management
# | Prompt Name | Purpose | Use Case | AI Compatibility
1 | Stakeholder Identification Prompt | Identify all stakeholders for a project | Project kick-off, stakeholder analysis | ChatGPT, Claude, Gemini, Copilot, Perplexity
2 | Power-Interest Matrix Generator | Map stakeholders on a Power-Interest matrix | Stakeholder engagement planning, communication strategy | ChatGPT, Claude, Gemini, Copilot, Perplexity
3 | Stakeholder Register Builder | Build a comprehensive stakeholder register | Project documentation, governance, BA planning | ChatGPT, Claude, Gemini, Copilot, Perplexity
4 | RACI Matrix Generator | Create a RACI matrix for a project or process | Project governance, team alignment, decision-making | ChatGPT, Claude, Gemini, Copilot, Perplexity
5 | Stakeholder Engagement Plan | Create a stakeholder engagement plan | Communication planning, project governance | ChatGPT, Claude, Gemini, Copilot, Perplexity
6 | Stakeholder Interview Preparation | Prepare for a stakeholder interview | Elicitation planning, discovery sessions | ChatGPT, Claude, Gemini, Copilot, Perplexity
7 | Persona Creator | Create a detailed user persona | Product design, requirements gathering, UX analysis | ChatGPT, Claude, Gemini, Copilot, Perplexity
8 | Resistance Management Plan | Identify and manage stakeholder resistance | Change management, project delivery, stakeholder engagement | ChatGPT, Claude, Gemini, Copilot, Perplexity
9 | Communication Plan Builder | Build a stakeholder communication plan | Project governance, team alignment, reporting structure | ChatGPT, Claude, Gemini, Copilot, Perplexity
10 | Stakeholder Conflict Resolver | Resolve conflicts between stakeholders | Requirements conflicts, priority disputes, scope disagreements | ChatGPT, Claude, Gemini, Copilot, Perplexity
11 | Stakeholder Analysis Report | Generate a stakeholder analysis report | Executive reporting, governance, project kick-off | ChatGPT, Claude, Gemini, Copilot, Perplexity
12 | Stakeholder Survey Designer | Design a stakeholder survey for requirement gathering | Large-scale elicitation, user research, feedback collection | ChatGPT, Claude, Gemini, Copilot, Perplexity
13 | Change Impact Assessment | Assess the impact of a change on stakeholders | Change management, impact analysis, communication planning | ChatGPT, Claude, Gemini, Copilot, Perplexity
14 | Stakeholder Sign-Off Preparation | Prepare stakeholders for document sign-off | Requirements baseline, BRD approval, UAT sign-off | ChatGPT, Claude, Gemini, Copilot, Perplexity
15 | Executive Briefing Preparer | Prepare an executive briefing on a project | Executive communication, status reporting, decision escalation | ChatGPT, Claude, Gemini, Copilot, Perplexity
16 | Stakeholder Feedback Analyzer | Analyze stakeholder feedback from reviews or surveys | Requirements refinement, retrospective analysis | ChatGPT, Claude, Gemini, Copilot, Perplexity
17 | Onboarding Stakeholder Brief | Create an onboarding brief for a new stakeholder | New stakeholder joining mid-project, team transitions | ChatGPT, Claude, Gemini, Copilot, Perplexity
18 | Stakeholder Escalation Path Designer | Design an escalation path for stakeholder issues | Governance, conflict resolution, project management | ChatGPT, Claude, Gemini, Copilot, Perplexity
19 | Meeting Agenda for Stakeholder Workshop | Create a professional meeting agenda for stakeholder sessions | Workshop planning, meeting facilitation | ChatGPT, Claude, Gemini, Copilot, Perplexity
20 | Stakeholder Training Needs Assessment | Assess training needs for stakeholders on a new system | Change management, go-live preparation, user adoption | ChatGPT, Claude, Gemini, Copilot, Perplexity

## Best Practices
Best Practices & Expert Tips — 02 Stakeholder Management
# | Prompt Name | Best Practice | Expert Tips
1 | Stakeholder Identification Prompt | Cast a wide net in the first pass. You can always narrow down — missing a stakeholder is harder to recover from. | Hidden stakeholders (legal, compliance, support) are the ones who derail projects. Find them early.
2 | Power-Interest Matrix Generator | Update the matrix monthly — stakeholder power and interest shift during projects. | The most dangerous stakeholder is the one in 'Monitor' who suddenly moves to 'Manage Closely.' Check this monthly.
3 | Stakeholder Register Builder | Keep the register updated as a living document. Assign an owner for each stakeholder. | A stale stakeholder register is worse than no register. Review and update it monthly.
4 | RACI Matrix Generator | Every activity must have exactly one A (Accountable). Multiple R's are fine, but no R means work won't get done. | RACI without a conversation is just a spreadsheet. Validate it with the team in a meeting.
5 | Stakeholder Engagement Plan | Engagement plans must be reviewed and updated at each project phase. | Engagement is not communication — it's two-way. Build feedback loops into your plan.
6 | Stakeholder Interview Preparation | Send the agenda in advance. Take a note-taker if possible. Never lead with solution ideas. | The best interview question is 'Can you walk me through a typical day/week doing this?' — it reveals everything.
7 | Persona Creator | Validate personas with real users — don't create them from assumptions alone. | Personas turn abstract users into real people — they make requirements conversations much richer.
8 | Resistance Management Plan | Resistance is almost never about the technology — it's about people's fears. Address the person, not the position. | Resistant stakeholders who become champions are your most powerful advocates. Invest time in them.
9 | Communication Plan Builder | Communication plans must match the recipient's preference — some executives want a 1-page summary, not a 10-page report. | Over-communication on big projects is almost impossible. Under-communication is very easy.
10 | Stakeholder Conflict Resolver | Never take sides in a stakeholder conflict. Present options with trade-offs. Let the sponsor decide. | Most stakeholder conflicts are about fear and control, not the actual requirement. Listen for what's unsaid.
11 | Stakeholder Analysis Report | Keep executive reports to 1-2 pages. Append detail in annexes. | A stakeholder analysis is not a one-time exercise. Repeat it at every project phase.
12 | Stakeholder Survey Designer | Keep surveys under 10 minutes. Pilot test with 2-3 users before sending. | Open-ended questions give you insight. Closed questions give you data. You need both.
13 | Change Impact Assessment | Always quantify the impact — number of people affected, process steps changed, training hours needed. | Impact assessment without a management plan is just a warning. Always follow up with action.
14 | Stakeholder Sign-Off Preparation | Set a deadline and a reminder. Never leave sign-off open-ended. | No sign-off = no baseline. No baseline = unlimited scope creep.
15 | Executive Briefing Preparer | Executives read the first 3 sentences and the last bullet. Make them count. | Never bring a problem to an executive without a recommendation. Even if you're not sure, present your best option.
16 | Stakeholder Feedback Analyzer | Quantify feedback where possible. Track themes across multiple feedback cycles. | Feedback is a gift. The stakeholders who complain are telling you how to succeed.
17 | Onboarding Stakeholder Brief | Send the onboarding brief 48h before the stakeholder's first meeting. | A well-onboarded stakeholder becomes an asset. A poorly onboarded one becomes a problem.
18 | Stakeholder Escalation Path Designer | Escalation paths prevent issues from dying in inbox limbo. Document and publish them. | Escalation is not failure — it's governance. Build it in from day one.
19 | Meeting Agenda for Stakeholder Workshop | Send agenda 48h in advance. Assign pre-read materials. Keep to schedule ruthlessly. | A meeting without an agenda is just a conversation. A meeting with a great agenda is where requirements get made.
20 | Stakeholder Training Needs Assessment | Always pilot training with a small group first. Gather feedback before rolling out. | Training without follow-up support leads to adoption failure. Build a help desk and FAQ alongside training.