## Cover
[COMPANY LOGO PLACEHOLDER]
RACI Matrix
Roles, Responsibilities & Accountability Framework
Organization: | [Organization Name]
Prepared by: | [Business Analyst Name]
Version: | 1.0
Date: | June 2025
Status: | Draft
Design & Prepared by: | Ahmed El Sayyad

## RACI Matrix
Activity / Deliverable | Phase | Project Sponsor | Project Manager | Business Analyst | IT Lead | Business Owner | End Users | QA/Test Lead | Change Manager
Project Charter | Initiation | A | R | C | I | C | I | I | I
Business Requirements Document | Planning | A | I | R | C | C | C | I | I
Stakeholder Analysis | Planning | I | C | R | I | A | I | I | C
Gap Analysis | Planning | A | I | R | C | C | I | I | I
Solution Design | Design | I | A | C | R | C | C | I | I
Technical Architecture | Design | I | A | I | R | I | I | I | I
UAT Test Cases | Testing | I | A | R | C | C | C | R | I
UAT Execution | Testing | A | I | C | C | R | R | C | I
Training Delivery | Deployment | I | A | C | I | C | R | I | R
Go-Live Approval | Deployment | R | A | C | C | C | I | C | C
Benefits Realization Review | Post-Launch | A | I | R | I | R | I | I | I

## RACI Legend
RACI Legend
R | Responsible | Person who executes the task. Must have at least one R per row.
A | Accountable | Person ultimately accountable. Only ONE A per row.
C | Consulted | Person who provides input before/during task execution.
I | Informed | Person who is notified of progress/outcomes after task completion.