## Assumption Log
ID | Category | Assumption Statement | Basis/Source | Impact if Invalid | Probability of Being Wrong | Impact Level | Owner | Validation Method | Validation Date | Status | Notes
ASS-001 | Technical | Current infrastructure can support new system without upgrade | IT infrastructure review Q1 2025 | High - significant cost and timeline impact | Low | High | [IT Lead] | Technical architecture review | 15/06/2025 | Open
ASS-002 | People | End users have sufficient computer literacy to use the system with training | HR competency assessment | Medium - additional training investment required | Low | Medium | [HR] | Pilot group assessment | 30/06/2025 | Validated | Confirmed by pilot
ASS-003 | Process | Existing data is clean enough for migration without major cleansing | Data quality report Q4 2024 | High - data migration effort significantly impacted | Medium | High | [Data Lead] | Data quality audit | 01/07/2025 | At Risk | Initial sampling shows issues
ASS-004 | Business | Budget will remain stable for project duration | Finance approval - Board minutes | High - scope reduction required | Low | High | [CFO] | Quarterly finance review | Ongoing | Validated
Design & Prepared by: | Ahmed El Sayyad