## Dependency Log
Dep ID | Dependency Name | Type | Description | Dependent Item | Depends On | Dependency Owner | Impact if Not Met | Probability | Impact Level | Target Resolution Date | Status | Mitigation Plan | Notes
DEP-001 | ERP Integration | Technical | New system requires live integration with ERP for real-time data | Real-time data features (FR-015 to FR-020) | ERP API availability & documentation | [IT Lead] | High - core features unavailable | Medium | High | 15/07/2025 | Open | Initiate ERP API access request; confirm documentation | Waiting for IT confirmation
DEP-002 | Infrastructure Upgrade | Technical | Server capacity upgrade required before UAT | UAT environment setup | Infrastructure procurement approval | [IT Infrastructure] | High - UAT delayed | Low | High | 30/06/2025 | In Progress | Approval submitted; procurement in process | Expected completion 25/06
DEP-003 | GDPR Legal Review | Compliance | Legal review of data handling approach required | Data storage and processing features | Legal team availability and review | [Legal] | High - compliance risk | Low | Critical | 01/07/2025 | Open | Meeting scheduled with Legal on 20/06 | GDPR consultant engaged
DEP-004 | Business Owner Sign-Off on BRD | Process | BRD approval required before design begins | Solution design phase start | Business owner availability for review | [Business Owner] | Medium - design phase delayed | Low | Medium | 20/06/2025 | In Progress | Review meeting scheduled; 2 sections outstanding | On track
Design & Prepared by: | Ahmed El Sayyad