## Cover
[COMPANY LOGO PLACEHOLDER]
Requirement Change Log
Change Request Tracking & Impact Management
Organization: | [Organization Name]
Prepared by: | [Business Analyst Name]
Version: | 1.0
Date: | June 2025
Status: | Draft
Design & Prepared by: | Ahmed El Sayyad

## Change Log
CR ID | Date Raised | Raised By | Change Description | Affected Requirements | Change Type | Justification | Scope Impact | Cost Impact ($) | Timeline Impact (days) | Priority | Recommended Action | Decision | Decision By | Decision Date | Status
CR-001 | 01/06/2025 | [Requestor] | Add two-factor authentication requirement | BR-001, FR-001 | New Requirement | Security team mandated post-risk review | Minor | 15000 | 5 | High | Approve - security risk warrants inclusion | Approved | [Decision Maker] | 05/06/2025 | Approved
CR-002 | 03/06/2025 | [Requestor] | Add mobile responsive design to all screens | FR-002 through FR-015 | Enhancement | Users primarily on mobile devices | Major | 45000 | 15 | Medium | Defer to Phase 2 - significant effort | Deferred | [Decision Maker] | 08/06/2025 | Deferred
CR-003 | 05/06/2025 | [Requestor] | Change report format from PDF to Excel export | FR-012 | Modification | End users prefer Excel for further analysis | Minor | 3000 | 2 | Low | Approve - low effort, high user value | Approved | [Decision Maker] | 07/06/2025 | Approved