## Cover
[COMPANY LOGO PLACEHOLDER]
Risk Assessment Matrix
Project Risk Register & Management
Organization: | [Organization Name]
Prepared by: | [Business Analyst Name]
Version: | 1.0
Date: | June 2025
Status: | Draft
Design & Prepared by: | Ahmed El Sayyad

## Risk Register
Risk ID | Risk Category | Risk Description | Cause | Effect/Impact | Probability (1-5) | Impact (1-5) | Risk Score | Risk Level | Current Controls | Mitigation Strategy | Contingency Plan | Risk Owner | Due Date | Status | Residual Risk
R-001 | Schedule | Key stakeholders unavailable during requirements phase | Competing business priorities | Requirements delayed; scope uncertainty | 3 | 4 |  |  | Calendar invites sent; priority set | Identify deputies; flexible scheduling | Use documented questions if unavailable | [Owner] | 30/06/2025 | Open | Medium
R-002 | Scope | Scope creep from uncontrolled change requests | Stakeholders requesting new features post-baseline | Budget overrun; timeline extension | 4 | 4 |  |  | Change control process in place | Strict change review board; impact assessment for all changes | Defer to Phase 2; adjust contingency budget | [Owner] | Ongoing | Open | Medium
R-003 | Technical | Integration with legacy system fails | Technical incompatibility; API limitations | Core functionality unavailable; go-live delay | 2 | 5 |  |  | Technical spike planned | Early proof-of-concept testing; fallback middleware | Manual interim process if integration fails | [IT Lead] | 15/07/2025 | Open | Low
R-004 | People | User resistance to new system | Change fatigue; poor change management | Low adoption; benefits not realized | 3 | 3 |  |  | Change management plan in development | Champion network; early user involvement; training | Supplemental training; hand-holding support | [Change Mgr] | 01/08/2025 | Open | Low