## Cover
[COMPANY LOGO PLACEHOLDER]
Defect Log
UAT Defect Tracking & Management
Organization: | [Organization Name]
Prepared by: | [Business Analyst Name]
Version: | 1.0
Date: | June 2025
Status: | Draft
Design & Prepared by: | Ahmed El Sayyad

## Defect Log
Defect ID | Title | Test Case ID | Requirement ID | Severity | Priority | Status | Description | Steps to Reproduce | Expected | Actual | Module/Area | Reported By | Report Date | Assigned To | Due Date | Resolution Date | Resolution Notes
DEF-001 | Login button unresponsive on mobile | TC-001 | FR-001 | P1 - Critical | High | Open | Login button does not respond to touch on mobile devices | 1. Open app on iOS 2. Enter credentials 3. Tap Login | User logged in successfully | Nothing happens | Authentication | [Reporter] | 01/06/2025 | [Dev] | 03/06/2025
DEF-002 | Password reset email delayed > 10 mins | TC-003 | FR-002 | P2 - High | Medium | In Fix | Password reset emails taking longer than specified 2 minute SLA | 1. Click Forgot Password 2. Enter email 3. Submit 4. Wait for email | Email received within 2 minutes | Email received after 12 minutes | Email Service | [Reporter] | 01/06/2025 | [Dev] | 05/06/2025 |  | Email queue backlog identified
DEF-003 | Report date filter shows incorrect results | TC-003 | BR-002 | P2 - High | High | Open | Date range filter on reports returns data outside selected range | 1. Go to Reports 2. Set date range 01/05 - 31/05 3. Generate report | Only data from May shown | Data from April also included | Reporting | [Reporter] | 02/06/2025 | [Dev] | 06/06/2025