## Cover
[COMPANY LOGO PLACEHOLDER]
Benefits Register
Benefits Realization Tracking & Management
Organization: | [Organization Name]
Prepared by: | [Business Analyst Name]
Version: | 1.0
Date: | June 2025
Status: | Draft
Design & Prepared by: | Ahmed El Sayyad

## Benefits Register
Benefit ID | Benefit Name | Category | Description | Type | Measurement Metric | Baseline Value | Target Value | Target Date | Benefit Owner | Realization Phase | Yr 1 Forecast ($) | Yr 2 Forecast ($) | Yr 3 Forecast ($) | Total Forecast ($) | Actual Yr 1 ($) | Status
BEN-001 | Process Efficiency Gains | Cost Reduction | Reduction in manual processing hours | Financial | Hours saved per week | 40 hrs/wk | 8 hrs/wk | Q4 2025 | [Owner] | Phase 1 | 150000 | 200000 | 250000 |  | 0 | On Track
BEN-002 | Error Reduction | Quality Improvement | Reduction in data entry errors and rework | Financial | Error rate % | 5% | 0.5% | Q1 2026 | [Owner] | Phase 1 | 80000 | 100000 | 120000 |  | 0 | On Track
BEN-003 | Customer Satisfaction Improvement | Revenue Enhancement | Higher CSAT leads to reduced churn | Financial | CSAT Score | 3.8/5.0 | 4.5/5.0 | Q2 2026 | [Owner] | Phase 2 | 50000 | 100000 | 150000 |  | 0 | Planned
BEN-004 | Compliance Risk Reduction | Risk Avoidance | Reduced regulatory fine exposure | Non-Financial | Audit findings | 8 findings/yr | 1 finding/yr | Q4 2025 | [Owner] | Phase 1 | 50000 | 50000 | 50000 |  | 0 | On Track
TOTAL