## Value vs Effort Matrix
Item ID | Initiative / Feature | Category | Business Value (1-10) | Implementation Effort (1-10) | Strategic Fit (1-10) | Risk Level | Value Score | Effort Score | Priority Quadrant | Recommended Action | Status
VE-001 | Automated approval workflows | Process | 9 | 3 | 8 | Low |  |  |  | Prioritize - high value, low effort | Approved
VE-002 | Real-time reporting dashboard | Analytics | 8 | 5 | 9 | Medium |  |  |  | Prioritize - strategic value | Approved
VE-003 | Mobile application | UX | 7 | 8 | 6 | High |  |  |  | Defer to Phase 2 | Deferred
VE-004 | Email notification system | Communication | 7 | 2 | 7 | Low |  |  |  | Quick win - implement immediately | Approved
VE-005 | AI-powered analytics | Innovation | 6 | 9 | 8 | High |  |  |  | Future roadmap - Phase 3 | Backlog
VE-006 | Single sign-on (SSO) | Security | 5 | 4 | 6 | Low |  |  |  | Fill-in - schedule when capacity permits | Backlog
VE-007 | Advanced audit trail | Compliance | 8 | 3 | 9 | Low |  |  |  | Quick win - compliance requirement | Approved
Design & Prepared by: | Ahmed El Sayyad

## Priority Grid
VALUE vs EFFORT PRIORITY GRID
|  | LOW EFFORT | HIGH EFFORT
| HIGH VALUE | QUICK WINS High value, low effort Do these first! | STRATEGIC BETS High value, high effort Schedule carefully
| LOW VALUE | FILL-INS Low value, low effort Do if capacity allows | AVOID Low value, high effort Eliminate or defer